## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - II | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 13/10/2024 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 23
2 | HOOGHLY | Khanakul - II | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000842/2023-2024 | 722/HUG | 05/03/2024 | 04/05/2024 | ANIRUDDHA FARUQUE | 48.17 | 6.8 | 14.12 | 100
3 | HOOGHLY | Khanakul - II | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1234/40/Hug | 28/04/2023 |  | Resource Division | 120.19 | 0 | 0 | 0
4 | HOOGHLY | Khanakul - II | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 1385/44/Hug | 15/05/2023 |  | Resource Division | 12.89 | 0 | 0 | 0
5 | HOOGHLY | Khanakul - II | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Material Requisition To Resource Division |  |  | RTOR000483/2023-2024 | 3057/5/Hug | 11/10/2023 |  | Resource Division | 12.89 | 0 | 0 | 0
6 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13762). Application No-5004034769 Reference Id-503576011 |  |  | BILL/00150/2024-2025 | 53 | 12/04/2024 |  | WBSEDCL | 3.94 | 0 | 0 | null
7 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13762) Application no-5004034787 Reference Id-503576010 |  |  | BILL/00440/2024-2025 | 127 | 17/05/2024 |  | WBSEDCL | 6.13 | 0 | 0 | null
8 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Quotation money deposition for new service connection at Hirapur w/s scheme, Zone- II, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004210670 Reference ID- 503656455 SM Code- 13762 |  |  | BILL/00820/2024-2025 | 222 | 18/06/2024 |  | WBSEDCL | 3.09 | 0 | 0 | null
9 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01122/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 105.92 | 0 | 0 | 0
10 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000150/2024-2025 | 1173/ED | 14/06/2024 | 12/09/2024 | PS & ASSOCIATES | 10.75 | 0 | 0 | 0
11 | HOOGHLY | Khanakul - II | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/13762 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000187/2022-2023 | 780/ED | 09/02/2023 | 10/05/2023 | M.D ENTERPRISE | 20.49 | 0 | 0 | 0
Total | [13 empty] | 6087.5 | 6.8 | 0.11