## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 25/10/2024 | M/S PRITI ENTERPRISE | 4251.5 | 0 | 0 | 17
2 | HOOGHLY | Goghat - II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 04/05/2024 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 0 | 0 | 0
3 | HOOGHLY | Goghat - II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1234/30/Hug | 28/04/2023 |  | Resource Division | 25.45 | 0 | 0 | 0
4 | HOOGHLY | Goghat - II | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Material Requisition To Resource Division |  |  | RTOR000493/2023-2024 | 3057/60/Hug | 11/10/2023 |  | Resource Division | 13.4 | 0 | 0 | 0
5 | HOOGHLY | Goghat - II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01122/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 105.92 | 0 | 0 | 0
6 | HOOGHLY | Goghat - II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034192 Reference Id-503574969. |  |  | BILL/06201/2023-2024 | 810 | 28/02/2024 |  | WBSEDCL | 4.41 | 0 | 0 | null
7 | HOOGHLY | Goghat - II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034199 Reference Id-503574970 |  |  | BILL/06202/2023-2024 | 809 | 28/02/2024 |  | WBSEDCL | 4.48 | 0 | 0 | null
8 | HOOGHLY | Goghat - II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000140/2024-2025 | 1166/ED | 14/06/2024 | 12/09/2024 | S.S. ENTERPRISES | 10.95 | 0 | 0 | 0
9 | HOOGHLY | Goghat - II | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000181/2022-2023 | 774/ED | 09/02/2023 | 10/05/2023 | S S ENTERPRISES | 22.09 | 0 | 0 | 10
Total | [13 empty] | 4502.52 | 0 | 0