## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | DAHAR KUNDU(ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly.[NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000153/2023-2024 | 1567/HUG | 29/05/2023 | 19/11/2024 | ASIA CONSTRUCTION | 365.13 | 209.37 | 57.34 | 30
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | Material Requisition To Resource Division |  |  | RTOR000491/2023-2024 | 3057/3/Hug | 11/10/2023 |  | Resource Division | 8.14 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-I,TW No-II Block-Arambag,Dist-Hooghly under Electrical Division PHE Dte. |  |  | BILL/03883/2023-2024 | 312 | 27/09/2023 |  | WBSEDCL | 8.01 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | Quotation Bill for New Service Connection at Daharkundu W/S. Sch. Z-I. TW-I |  |  | BILL/04085/2023-2024 | 354 | 12/10/2023 |  | WBSEDCL | 4.97 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/14983 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-I, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000172/2022-2023 | 765/ED | 09/02/2023 | 10/05/2023 | POLYCON ENGINEERS | 20.39 | 10.11 | 49.6 | 30
Total | [13 empty] | 504.28 | 219.48 | 43.52