## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | BIGHATI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under SINGUR Block, District- Hooghly.[NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2023-2024 | 1061/HUG | 12/04/2023 | 07/01/2024 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 422.23 | 195.08 | 46.2 | 85
2 | HOOGHLY | Singur | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | Sinking of 1no. tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at BIGHAT ZONE - II Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly |  |  | ORD/000057/2024-2025 | 2367/HUG | 21/06/2024 | 21/07/2024 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 31.59 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 1383/21/Hug | 15/05/2023 |  | Resource Division | 9.73 | 0 | 0 | 0
4 | HOOGHLY | Singur | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | Material Requisition To Resource Division |  |  | RTOR000424/2023-2024 | 3058/23/Hug | 11/10/2023 |  | Resource Division | 9.73 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | Quotation bill of WBSEDCL security deposit for Bighati PWSS, TW No.- II |  |  | BILL/04478/2023-2024 | 524 | 13/12/2023 |  | WBSEDCL | 4.06 | 0 | 0 | 0
6 | HOOGHLY | Singur | Electrical | Ground Water Based Bighati (Zone -II) PWSS | SM/15249 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 04/06/2023 | ORIENTAL ENGINEERING CO. | 40.49 | 6.38 | 15.76 | 80
Total | [13 empty] | 517.82 | 201.46 | 38.91