## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer |  | ORD/000164/2023-2024 | 1618/Hug | 02/06/2023 | 27/02/2024 | M/S RAJKUMAR KHAN | 246.71 | 6.63 | 2.69 | 15
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000179/2023-2024 | 1618/hug | 02/06/2023 | 27/02/2024 | M/S RAJKUMAR KHAN | 246.71 | 38.31 | 15.53 | 20
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 1385/57/Hug | 15/05/2023 |  | Resource Division | 6.12 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Material Requisition To Resource Division |  |  | RTOR000472/2023-2024 | 3057/12/Hug | 11/10/2023 |  | Resource Division | 6.12 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=II |  |  | BILL/04611/2023-2024 | 610 | 04/01/2024 |  | WBSEDCL | 6.44 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000025/2023-2024 | 1702/ED | 18/04/2023 | 17/07/2023 | NUPUR CHANDRA HALDER | 20.8 | 0 | 0 | 0
Total | [13 empty] | 604.06 | 44.94 | 7.44