## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions at Itkhola for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2024-2025 | 537/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 2.81 | 2.81 | 99.95 | 100
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions of Payan majipara for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000036/2024-2025 | 538/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 99.91 | 100
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions of Priyanagar for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000037/2024-2025 | 539/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 99.94 | 85
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Repairing Of Switch Room, Boundary wall for Badinan W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000061/2024-2025 | 2408/HUG | 26/06/2024 | 26/07/2024 | GHOSH CONSTRUCTION | 7.86 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Preparation of DPR for Augmentation Hanral Z-I Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000075/2024-2025 | 690/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 3.88 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of BADINAN W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000082/2023-2024 | 1337/HUG | 11/05/2023 | 25/06/2023 | BAKSHI ENTERPRISE | 40.42 | 17.74 | 43.89 | 45
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at BADINAN W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000603/2023-2024 | 3318/HUG | 10/11/2023 | 10/12/2023 | AUXILIARY TUBEWELL DRILLERS | 14.88 | 6.53 | 43.89 | 100
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 0 | 0 | 65
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Badinan PWSS 2. Hanral PWSS 3. Rajhat PWSS 4. Dibur Bheri PWSS 5. Akna PWSS 6. Harit PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000823/2023-2024 | 201/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 50
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Laying HDPE Pipeline from newly bored tube well to existing distribution system at PAYAN of BADINAN water supply scheme under Chinsurah Sub-Division under Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000844/2023-2024 | 731/HUG | 05/03/2024 | 04/04/2024 | BIMAL KUMAR HALDER | 17.98 | 12.34 | 68.64 | 50
11 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Additional Quotation for new service connection at Badinan w/s sch. , P.H. No. III, Dist -Hooghly |  |  | BILL/00750/2023-2024 | 37 | 15/05/2023 |  | WBSEDCL | 0.48 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Quatation bill for New service connection at Aug. of Badinan w/s scheme, P.H No.-3 |  |  | BILL/00871/2022-2023 | 176 | 02/03/2023 |  | WBSEDCL | 4.74 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Quotation Bill for New Service Connection at Badinan W/S. Sch. TW-I |  |  | BILL/04640/2023-2024 | 632 | 08/01/2024 |  | WBSEDCL | 5.16 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000012/2023-2024 | 1628/ED | 11/04/2023 | 10/07/2023 | BIDYUT KUMAR MUKHERJEE | 11.41 | 2.74 | 23.97 | 99
17 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Badinan water supply scheme, T.W. No. III, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000124/2022-2023 | 3480/ED | 30/12/2022 | 30/03/2023 | INDIA ENTERPRISE | 10.64 | 5.15 | 48.39 | 90
18 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000864/2023-2024 | 3436/ED | 11/08/2023 | 09/11/2023 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 0 | 0
Total | [13 empty] | 382.91 | 56.99 | 14.88