## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of RADHABALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000145/2023-2024 | 1498/HUG | 22/05/2023 | 21/06/2023 | P.K. GHOSH & CO. | 11.83 | 3.96 | 33.45 | 85
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at RADHABALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/000763/2022-2023 | 747/HUG | 15/03/2023 | 14/04/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 10.28 | 90.77 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Quotation of New Service Connection for Radhaballavpur w/s Scheme, TW No-3 Dist- Hooghly under ED,PHE Dte |  |  | BILL/02131/2023-2024 | 117 | 20/07/2023 |  | WBSEDCL | 2.82 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Radhaballabpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000006/2023-2024 | 1622/ED | 11/04/2023 | 10/07/2023 | M/S, GHOSH ENTERPRISE | 10.74 | 5.33 | 49.61 | 40
Total | [13 empty] | 107.88 | 19.57 | 18.14