## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | SM/15806 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within ARAMBAGH Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000144/2023-2024 | 1497/HUG | 22/05/2023 | 21/06/2023 | DEBANANDA CONSTRUCTION | 11.81 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | SM/15806 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PURBARAYPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte | Assistant Engineer |  | ORD/000762/2022-2023 | 746/HUG | 15/03/2023 | 14/04/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | SM/15806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1263/11/Hug | 03/05/2023 |  | Resource Division | 5.69 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | SM/15806 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | SM/15806 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Purba Raypur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000005/2023-2024 | 1621/ED | 11/04/2023 | 10/07/2023 | ESENCE ENGINEERING CONCERN | 10.75 | 0 | 0 | 0
Total | [13 empty] | 110.74 | 0 | 0