## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Laying of pipe line for left out portion within command area of Jaykrishnapur Water Supply Scheme to facilate the FHTC Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000041/2023-2024 | 1170/HUG | 20/04/2023 | 20/05/2023 | SADHUKHAN ENTERPRISE | 4.76 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Jaykrishnapur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000141/2023-2024 | 1494/HUG | 22/05/2023 | 21/06/2023 | A.R. CONSTRUCTION | 11.83 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JAYKRISHNAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000774/2022-2023 | 746/hug | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 5.29 | 46.72 | 100
4 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Quotation of New Service Connection for Jaykrishnapur w/s Scheme,TW no-3 Block-Goghat-I Dist-Hooghly under ED,PHE Dte(SM/15808) Application No-5004009573 Reference Id-503561825 |  |  | BILL/06051/2023-2024 | 748 | 16/02/2024 |  | WBSEDCL | 3.95 | 0 | 0 | null
6 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000865/2023-2024 | 3438/ED | 11/08/2023 | 09/11/2023 | J.K. ENGINEERING CO. | 10.74 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001150/2022-2023 | 1502/ED | 28/03/2023 | 26/06/2023 | M/S DILIP MITRA | 10.75 | 0 | 0 | 0
Total | [13 empty] | 124.51 | 5.29 | 4.25