## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangment , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of GANESHBATI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer |  | ORD/000194/2023-2024 | 1779/HUG | 15/06/2023 | 15/07/2023 | ROY ENTERPRISE | 12.01 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at GANESHBATI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000745/2022-2023 | 656/HUG | 09/03/2023 | 23/04/2023 | R CONSTRUCTION | 22.63 | 13.05 | 57.69 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2022-2023 | 1263/14/Hug | 03/05/2023 |  | Resource Division | 11.5 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Quotation for New Service Connection of Ganeshbati W/S Scheme(Aug) TW No-4 District-Hooghly under Electrical Division PHE Dte. |  |  | BILL/00754/2023-2024 | 42 | 17/05/2023 |  | WBSEDCL | 3.31 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Ganeshbati water supply scheme, T.W. No. I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001148/2022-2023 | 1500/ED | 28/03/2023 | 26/06/2023 | ASHUTOSH DAS & CO. | 21.49 | 0 | 0 | 0
Total | [13 empty] | 142.1 | 13.05 | 9.18