## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 25/10/2024 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
2 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 25/10/2024 | M/S PRITI ENTERPRISE | 4251.5 | 0 | 0 | 17
3 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Lying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SAMANTAKHANDA (1no.), SELAMPUR Z-I (1no.), SANTIPUR Z-I (1no.), SELAMPUR Z-II (1no.) and GARMANDARAN Z-I (1No.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION). |  |  | ORD/000793/2023-2024 | 542/HUG | 20/02/2024 | 20/04/2024 | M/S SREEJIT ENTERPRISE | 59.07 | 0 | 0 | 0
4 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 04/05/2024 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
5 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1234/26/Hug | 28/04/2023 |  | Resource Division | 51.53 | 0 | 0 | 0
6 | HOOGHLY | Goghat - II | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Material Requisition To Resource Division |  |  | RTOR000389/2023-2024 | 3057/57/Hug | 11/10/2023 |  | Resource Division | 17.57 | 0 | 0 | 0
7 | HOOGHLY | Goghat - II | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
8 | HOOGHLY | Goghat - II | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Quotation of New Service Connection for Samanta Khanda w/s Scheme, PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/16127) Application No-5004034170 Reference Id-503574968 |  |  | BILL/06199/2023-2024 | 814 | 28/02/2024 |  | WBSEDCL | 4.75 | 0 | 0 | null
9 | HOOGHLY | Goghat - II | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAMANTA KHANDA PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000137/2024-2025 | 1163/ED | 14/06/2024 | 12/09/2024 | PADMA ENGINEERING CO. | 10.74 | 0 | 0 | 0
10 | HOOGHLY | Goghat - II | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME | SM/16127 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanta Khanda water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000311/2022-2023 | 1241/ED | 06/03/2023 | 04/06/2023 | R.M.D TRADING. | 22.84 | 0 | 0 | 0
Total | [13 empty] | 4628.38 | 0 | 0