## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - II | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/16237 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 1385/10/Hug | 15/05/2023 |  | Resource Division | 0.47 | 0 | 0 | 0
2 | HOOGHLY | Khanakul - II | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/16237 | New | Material Requisition To Resource Division |  |  | RTOR000409/2023-2024 | 3057/59/Hug | 11/10/2023 |  | Resource Division | 0.76 | 0 | 0 | 0
3 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/16237 | New | Quotation of new service Connection for Naopara w/s Scheme,PH No-I Block-Khanakul-II, Dist-Hooghly under ED,PHE Dte(SM/16237) Application No-5004015680 Reference Id-503563156 |  |  | BILL/06072/2023-2024 | 751 | 16/02/2024 |  | WBSEDCL | 0.2 | 0 | 0 | null
4 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/16237 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NAOPARA MINI W/S SCHEME, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000168/2024-2025 | 1191/ED | 14/06/2024 | 12/09/2024 | MAA TARA CONSTRUCTION | 7.52 | 5.49 | 73.03 | 30
Total | [13 empty] | 8.96 | 5.49 | 61.31