## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC For Development of JANGALPARA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000110/2023-2024 | 1439/HUG | 18/05/2023 | 02/07/2023 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 35.13 | 17.7 | 50.38 | 20
2 | HOOGHLY |  | Hooghly Division | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 1384/22/Hug | 15/05/2023 |  | Resource Division | 2.77 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | Quotation bill for new service connection at Jangalpara W/S. Sch. PH-III |  |  | BILL/00727/2023-2024 | 34 | 12/05/2023 |  | WBSEDCL | 2.96 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | New service connection charges for Jangalpara w/s scheme, PH No.-III |  |  | BILL/01159/2023-2024 | 87 | 12/07/2023 |  | WBSEDCL | 0.53 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | New service connection charges for Jangalpara w/s scheme, PH No.-III |  |  | BILL/01160/2023-2024 | 85 | 12/07/2023 |  | WBSEDCL | 2.95 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | SM/16448 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangalpara water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001149/2022-2023 | 1501/ED | 28/03/2023 | 26/06/2023 | INDRANI ENTERPRISE | 10.75 | 10.44 | 97.1 | 75
Total | [13 empty] | 55.09 | 28.13 | 51.07