## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in left out portion of BANDIPUR PWSS, Block. HARIPAL under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000042/2023-2024 | 1171/HUG | 20/04/2023 | 04/06/2023 | TITAS CONSTRUCTION | 57.96 | 31.61 | 54.54 | 50
2 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Construction of 1 (One) No. Pump House (3.0 x 3.6 m ) with additional plinth height including internal pathway at 6th tubewell site of Bandipur PWSS Scheme under Hooghly Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000765/2022-2023 | 145/Chan | 16/03/2023 | 25/04/2023 | BMR ENGINEERING & CONSTRUCTION | 4.99 | 3.25 | 65.21 | 80
3 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of pump house at 2nd TW site of Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000946/2023-2024 | 285/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 1 | 0.97 | 97.86 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing of boundary wall at 2nd TW site of Bandipur Piped Water Supply Scheme Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000947/2023-2024 | 286/Chan | 15/03/2024 | 30/03/2024 | SHREE JAGANNATH ENTERPRISE | 0.99 | 0.99 | 99.25 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Laying of Rising main for Interconnection of Laying distribution system at 6th Tube well site of Bandipur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000949/2023-2024 | 287/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.92 | 0.89 | 96.82 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME | SM/16648 | Retrofitting | Repairing Damaged pipeline at Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000954/2023-2024 | 292/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.37 | 0.37 | 99.87 | 100
Total | [13 empty] | 66.23 | 38.09 | 57.51