## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | DHARMMAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000005/2023-2024 | 1017/Hug | 06/04/2023 | 01/01/2024 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 407.11 | 56.86 | 13.97 | 12
2 | HOOGHLY | Khanakul - I | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Material Requisition To Resource Division |  |  | RTOR000478/2023-2024 | 3057/9/Hug | 11/10/2023 |  | Resource Division | 12.23 | 0 | 0 | 0
3 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
4 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Quotation of New Service Connection For Dharmmapur w/s scheme,PH No-II Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte(SM/17716) Application no-5004012404 Reference Id-503561209 |  |  | BILL/06049/2023-2024 | 740 | 08/02/2024 |  | WBSEDCL | 3.59 | 0 | 0 | null
5 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Quotation of New Service Connection for Dharmmapur w/s Scheme,PH No-I Block-Khanakul-I Dist-Hooghly under ED,PHE Dte(SM/17716) Application No-5004012408 Reference Id-503561211 |  |  | BILL/06050/2023-2024 | 741 | 08/02/2024 |  | WBSEDCL | 5.64 | 0 | 0 | null
6 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/17716 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dharmmapur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000050/2023-2024 | 1794/ED | 24/04/2023 | 23/07/2023 | M/S, GHOSH ENTERPRISE | 20.35 | 0 | 0 | 0
Total | [13 empty] | 546.56 | 56.86 | 10.4