## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | NILARPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000230/2023-2024 | 2063/HUG | 17/07/2023 | 12/04/2024 | BANSBERIA CONSTRUCTION CO. | 411.87 | 57.05 | 13.85 | 40
2 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mundalika-I PWSS 2. Mundalika-II PWSS 3. Nilarpur PWSS 4. Gopalpur PWSS 5. Bishnupur PWSS 6. Radhanagar PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000944/2023-2024 | 114/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.48 | 50 | 80
3 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 1384/7/Hug | 16/05/2023 |  | Resource Division | 7.93 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Material Requisition To Resource Division |  |  | RTOR000510/2023-2024 | 3060/8/Hug | 11/10/2023 |  | Resource Division | 7.93 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. |  |  | BILL/04635/2023-2024 | 635 | 08/01/2024 |  | WBSEDCL | 4.83 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. PH-I |  |  | BILL/04638/2023-2024 | 634 | 08/01/2024 |  | WBSEDCL | 8.22 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | SM/18105 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nilarpur water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000073/2023-2024 | 1929/ED | 15/05/2023 | 13/08/2023 | SWAPAN ENTERPRISE | 23.08 | 11.25 | 48.72 | 90
Total | [13 empty] | 569.08 | 68.78 | 12.09