## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed T/W Site of UDAYPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000173/2024-2025 | 3171/HUG | 10/09/2024 | 10/10/2024 | OSMAN SEKH | 32.29 | 0 | 0 | 0
2 | HOOGHLY | Khanakul - I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 10/10/2024 | MACKINTOSH BURN LIMITED | 3480.01 | 0 | 0 | 15
3 | HOOGHLY | Khanakul - I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Material Requisition To Resource Division |  |  | RTOR000391/2023-2024 | 3057/56/Hug | 11/10/2023 |  | Resource Division | 19.7 | 0 | 0 | 0
4 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037021/Quot/03 Reference ID- 503576711 SM Code- 18308 |  |  | BILL/06215/2023-2024 | 818 | 03/03/2024 |  | WBSEDCL | 3.92 | 0 | 0 | null
5 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036968/Quot/03 Reference ID- 503576706 SM Code- 18308 |  |  | BILL/06216/2023-2024 | 819 | 01/03/2024 |  | WBSEDCL | 11.54 | 0 | 0 | null
6 | HOOGHLY | Khanakul - I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Udaypur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000817/2023-2024 | 3162/ED | 27/07/2023 | 25/10/2023 | DEBJYOTI BASU | 21.36 | 0 | 0 | 0
Total | [13 empty] | 3568.82 | 0 | 0