## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 10/10/2024 | MACKINTOSH BURN LIMITED | 3480.01 | 0 | 0 | 15
2 | HOOGHLY | Khanakul - I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000842/2023-2024 | 722/HUG | 05/03/2024 | 04/05/2024 | ANIRUDDHA FARUQUE | 48.17 | 0 | 0 | 100
3 | HOOGHLY | Khanakul - I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Material Requisition To Resource Division |  |  | RTOR000479/2023-2024 | 3057/8/Hug | 11/10/2023 |  | Resource Division | 11.45 | 0 | 0 | 0
4 | HOOGHLY | Khanakul - I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Quotation of New Service Connection for UDNA w/s Scheme, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18309) Application No-5004114171 Reference Id-503617472 |  |  | BILL/00233/2024-2025 | 83 | 22/04/2024 |  | WBSEDCL | 3.38 | 0 | 0 | null
5 | HOOGHLY | Khanakul - I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for UDNA water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000814/2023-2024 | 3159/ED | 27/07/2023 | 25/10/2023 | MAA KALI ENTERPRISE | 20.23 | 14.81 | 73.2 | 100
6 | HOOGHLY | Khanakul - I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Udna water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002471/2023-2024 | 332/ED | 21/02/2024 | 21/05/2024 | MAA KALI ENTERPRISE | 21.44 | 8.38 | 39.07 | 20
Total | [13 empty] | 3584.67 | 23.18 | 0.65