## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 25/10/2024 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Augmentation of KRISHNANAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls in ZONE-II & Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I under KHANAKUL-I Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000224/2023-2024 | 2036/HUG | 13/07/2023 | 08/04/2024 | M/S PRADYUT KUMAR HAZRA | 642.46 | 256.02 | 39.85 | 15
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2022-2023 | 79/22/Hug | 06/01/2023 |  | Resource Division | 38.01 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-I, Z-II |  |  | BILL/04317/2023-2024 | 426 | 17/11/2023 |  | WBSEDCL | 5.3 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-II, Z-II, |  |  | BILL/04318/2023-2024 | 425 | 17/11/2023 |  | WBSEDCL | 3.94 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000190/2024-2025 | 1205/ED | 14/06/2024 | 12/09/2024 | SWAPAN ENTERPRISE | 10.75 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. V, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000193/2024-2025 | 1207/ED | 14/06/2024 | 12/09/2024 | D.S. ENTERPRISE | 10.74 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnanagar water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000992/2023-2024 | 3788/ED | 26/09/2023 | 25/12/2023 | GLACIER ENGINEERING CO. | 21.75 | 10.85 | 49.9 | 40
Total | [13 empty] | 781.42 | 266.88 | 34.15