## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | RASULPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000256/2023-2024 | 2188/HUG | 26/07/2023 | 21/04/2024 | KHAN ENTERPRISE | 741.7 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Material Requisition To Resource Division |  |  | RTOR000400/2023-2024 | 3057/51/Hug | 11/10/2023 |  | Resource Division | 19.68 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000161/2024-2025 | 1184/ED | 14/06/2024 | 12/09/2024 | RISHAV ENTERPRISE | 10.75 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000162/2024-2025 | 1185/ED | 14/06/2024 | 12/09/2024 | M/S, GHOSH ENTERPRISE | 10.73 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
Total | [13 empty] | 793.28 | 0 | 0