## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000160/2023-2024 | 1618/HUG | 02/06/2023 | 17/07/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 12.25 | 16.82 | 65
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000221/2022-2023 | 226/1/Hug | 24/01/2023 |  | Resource Division | 178.88 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-III under Electrical Division,PHE Dte.(SM/18644). Application No-5004112076. Reference Id-503617154. |  |  | BILL/00190/2024-2025 | 78 | 19/04/2024 |  | WBSEDCL | 19.66 | 0 | 0 | null
4 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-IV under Electrical Division,PHE Dte.(SM/18644). Application No-5004111585. Reference Id-503617124. |  |  | BILL/00191/2024-2025 | 79 | 19/04/2024 |  | WBSEDCL | 7.52 | 0 | 0 | null
5 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of April 2024. |  |  | BILL/00501/2024-2025 | 154 | 28/05/2024 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | null
6 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Supply of Fuel for 1(One) no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE DTe. for the Month of May 2024. Car No-WB 04H 0517 |  |  | BILL/00715/2024-2025 | 226 | 18/06/2024 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | null
7 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Supply of Fuel for 1(one) no Diesel Luxury taxi on Contract Carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of June 2024. |  |  | BILL/01151/2024-2025 | 283 | 09/07/2024 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | null
8 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Supply of Fuel for 1(One) no. Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer,Howrah mechanical Sub Division,PHE Dte for the Month of July 2024. |  |  | BILL/01636/2024-2025 | 413 | 22/08/2024 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | null
9 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000002/2024-2025 | 2404/HMSD | 26/04/2024 | 26/09/2024 | ARINDAM AUDDY | 0.73 | 0.45 | 62.06 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bakulia water supply scheme, T.W. No. I & II, Block: Balagarh, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000926/2023-2024 | 3597/ED | 28/08/2023 | 26/11/2023 | R.M.D TRADING. | 21.89 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 29/04/2024 | ARINDAM AUDDY | 0.86 | 0.16 | 18.79 | 15
12 | HOOGHLY |  | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002957/2023-2024 | 2829_/HMSD | 30/10/2023 | 29/04/2024 | ARINDAM AUDDY | 0.86 | 0 | 0 | 0
Total | [13 empty] | 304.25 | 12.87 | 4.23