## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underKhanakul I & II &Goghat I & II Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000162/2024-2025 | 2831/HUG | 09/08/2024 | 24/08/2024 | HORIZEN | 1.6 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Augmentation of KHANAKUL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | Assistant Engineer |  | ORD/000304/2023-2024 | 2368/HUG | 08/08/2023 | 04/05/2024 | M/S. NANDY ENTERPRISE | 382.9 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Augmentation of KHANAKUL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000317/2023-2024 | 2392/HUG | 10/08/2023 | 06/05/2024 | SUBHANKAR BANERJEE | 387.3 | 21.84 | 5.64 | 15
4 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method , Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer |  | ORD/000812/2023-2024 | 592/HUG | 22/02/2024 | 22/04/2024 | TOTON MONDAL | 29.75 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000813/2023-2024 | 596/HUG | 22/02/2024 | 22/04/2024 | ANIRUDDHA FARUQUE | 29.6 | 13.16 | 44.44 | 50
6 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Quotation money deposition for new service connection at Khanakul W/S Zone- I ,T.W No.-I , Hooghly APP. No.- 5004036875 SM/18645 |  |  | BILL/06213/2023-2024 | 824 | 01/03/2024 |  | WBSEDCL | 4.35 | 0 | 0 | null
7 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Quotation money deposition for new service connection at khanakul w/s scheme, zone-II, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036737/Quot/03 Reference ID- 503576720 SM Code- 18645 |  |  | BILL/06214/2023-2024 | 823 | 01/03/2024 |  | WBSEDCL | 3.39 | 0 | 0 | null
8 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000157/2024-2025 | 1180/ED | 14/06/2024 | 12/09/2024 | M/S A.K BANERJEE | 10.73 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000158/2024-2025 | 1181/ED | 14/06/2024 | 12/09/2024 | M/S A.K BANERJEE | 10.74 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL | SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Khanakul water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000929/2023-2024 | 3600/ED | 28/08/2023 | 26/11/2023 | M/S S.R. ENTERPRISE | 21.49 | 0 | 0 | 0
Total | [13 empty] | 881.86 | 35 | 3.97