## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 24/01/2025 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | MAYAPUR Piped Water Supply Scheme with Sinking of tube-well, Rising Main & construction of boundary walls at different TW site under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000507/2023-2024 | 2916/HUG | 22/09/2023 | 17/03/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 72.39 | 0 | 0 | 35
3 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & Providing FHTC IN MAYAPUR Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000592/2023-2024 | 3187/HUG | 30/10/2023 | 01/01/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 212.41 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Laying Distribution System of proposed pipe line& construction of switch-rooms at different TW site of MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000593/2023-2024 | 3302/Hug | 10/11/2023 | 09/03/2024 | EQUIPMENTS AND SPARES AGENCIES | 197.56 | 95.62 | 48.4 | 30
5 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000931/2023-2024 | 987/HUG | 16/03/2024 | 15/04/2024 | BIBHUTI SHAW | 46.75 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Hooghly Division | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Material Requisition To Resource Division |  |  | RTOR000447/2023-2024 | 3057/26/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.6 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Quotation of New Service Connection for Mayapur w/s Scheme, PH No-II Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte. |  |  | BILL/00428/2024-2025 | 131 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.32 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Electrical | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. I, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000177/2024-2025 | 1201/ED | 14/06/2024 | 12/09/2024 | WIZARDTECH SOLUTION | 10.75 | 0 | 0 | 0
9 | HOOGHLY | Arambag | Electrical | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. II, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000185/2024-2025 | 1202/ED | 14/06/2024 | 12/09/2024 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
10 | HOOGHLY | Arambag | Electrical | Mayapur Piped Water Supply Scheme. | SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000186/2024-2025 | 1203/ED | 14/06/2024 | 12/09/2024 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
Total | [13 empty] | 635.76 | 95.62 | 15.04