## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Connection of T.W. No. III with distribution and Road crossing of Arambagh-Chapadanga Road for DIHI BAYRA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000652/2023-2024 | 3483/HUG | 29/11/2023 | 28/01/2024 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 6.86 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Dihibayra w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001527/2021-2022 | 544/HMSD | 17/03/2022 | 16/04/2022 | WIZARDTECH SOLUTION | 2.36 | 2.36 | 100 | 100
3 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibayra water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001532/2021-2022 | 471_ED | 10/03/2022 | 08/06/2022 | T S CONSTRUCTION | 6.4 | 2.02 | 31.55 | 50
Total | [13 empty] | 15.62 | 4.38 | 28.05