## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000303/2020-2021 | 1426/BQA | 09/10/2020 | 08/11/2020 | SUMITA UPADHYAY | 33.29 | 1.82 | 5.46 | 85
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280) & Dharampur (281) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000304/2020-2021 | 1427/BQA | 09/10/2020 | 08/11/2020 | MUNMUN UPADHYAY | 41.55 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) |  | Junior Engineer | ORD/000443/2020-2021 | 108/KSD | 11/02/2021 | 21/02/2021 | SUMITA UPADHYAY | 2.07 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Jetpara (280) & Dharampur (281) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) |  | Junior Engineer | ORD/000444/2020-2021 | 109/KSD | 11/02/2021 | 21/02/2021 | SUMITA UPADHYAY | 4.91 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Kumarpur (209) & Amdani (229) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) |  | Junior Engineer | ORD/000445/2020-2021 | 110/KSD | 11/02/2021 | 21/02/2021 | MUNMUN UPADHYAY | 4.93 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Kumarpur (209) & Amdani (229) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) |  | Junior Engineer | ORD/000446/2020-2021 | 111/KSD | 11/02/2021 | 21/02/2021 | MUNMUN UPADHYAY | 4.94 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Work Order for Household survey in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danrkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280), Dharampur (281) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 40) | Assistant Engineer | Junior Engineer | ORD/000542/2020-2021 | 282/KSD | 10/12/2020 | 08/02/2021 | TARINI CHARAN UPADHYAY | 0.32 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Laying extra UPVC pipe line to cover Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208)mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block - Sarenga, Dist- Bankura. |  |  | VCH/000017/2021-2022 | null | 12/04/2021 |  | SUMITA UPADHYAY | 2.07 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Laying extra UPVC pipe line to cover Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Jetpara (280), Bharampur (281) mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  |  | VCH/000018/2021-2022 | null | 12/04/2021 |  | SUMITA UPADHYAY | 4.91 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Laying extra UPVC pipe line to cover Construction and commissioning of FHTC (Functional Household Tap Connection) in Kumarpur (209), Ambani (229), mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  |  | VCH/000019/2021-2022 | null | 12/04/2021 |  | MUNMUN UPADHYAY | 4.92 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Laying extra UPVC pipe line to cover Kumarpur (209), Ambani (229), mouzas for Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas |  |  | VCH/000020/2021-2022 | null | 12/04/2021 |  | MUNMUN UPADHYAY | 4.94 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  |  | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 |  | EARTHMOVING (INDIA) | 27.48 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Radhanagar w/s scheme (zone - l) under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (Part - B) , total house hold -66 ( MB No - 3981)" |  |  | VCH/001546/2020-2021 | FHTC/276 | 08/02/2021 |  | I.R.CONSTRUCTION | 4.6 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part - A) , total house hold - 200 ( MB No - 4024)" |  |  | VCH/001547/2020-2021 | FHTC/276 | 08/02/2021 |  | SUBHANKAR BANERJEE | 13.81 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | "Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection)¿ in with Jal Jeavan Mission (JJM) and Jal swapan of Gadardihi (zone - E) under Bankura - l & ll & barjora block w/s scheme ( BRGF ph - l project ) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Block - Barjora, Name of OHR - Gadardihi (zone - E) no of mouza - 01 Gadardihi (Part -A) , total house hold - 145 ( MB No - 4024)" |  |  | VCH/001548/2020-2021 | FHTC/276 | 08/02/2021 |  | SUBHANKAR BANERJEE | 9.71 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (29) mouzas by retrofitting zone - llB of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B ( MB No - 3953) |  |  | VCH/001558/2020-2021 | FHTC/283 | 22/02/2021 |  | SUNIL KUMAR MANDAL | 3.27 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia (267) mouzas by retrofitting zone - llB of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A ( MB No - 3953) |  |  | VCH/001559/2020-2021 | FHTC/283 | 22/02/2021 |  | TAPAN KUMAR MANDAL | 3.9 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | SM/06790 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 |  | EARTH MOVING (INDIA) | 31.31 | 0 | 0 | 0
Total | [13 empty] | 202.92 | 1.82 | 0.9