## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000062/2020-2021 | 474/BQA | 05/02/2021 | 07/03/2021 | DEBAKI RANJAN SARKAR | 23.18 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Penchakola (298) & Dubli (299) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000294/2020-2021 | 1417/BQA | 09/10/2020 | 08/11/2020 | SIB SANKAR CHOWDHURY | 41.33 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000295/2020-2021 | 1418/BQA | 09/10/2020 | 08/11/2020 | SIB SANKAR CHOWDHURY | 39.24 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Penchakola (298) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) |  | Junior Engineer | ORD/000447/2020-2021 | 112/KSD | 11/02/2021 | 21/02/2021 | SIB SANKAR CHOWDHURY | 4.93 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Dubli (299) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  | Junior Engineer | ORD/000449/2020-2021 | 113/KSD | 11/02/2021 | 21/02/2021 | SIB SANKAR CHOWDHURY | 4.24 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Kharsasuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurbada (360) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 7) |  | Junior Engineer | ORD/000450/2020-2021 | 114/KSD | 11/02/2021 | 21/02/2021 | SIB SANKAR CHOWDHURY | 4.97 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Work Order for Household survey in Penchakola (298), Dubli (299), Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 33) |  | Junior Engineer | ORD/000536/2020-2021 | 275/KSD | 10/12/2020 | 08/02/2021 | SIB SANKAR CHOWDHURY | 0.4 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharkashuli (300), Marosol (302), Katalda (343), Baherbani (344) & Thakurabada (360) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3907) |  |  | VCH/001536/2020-2021 | FHTC/280 | 12/02/2021 |  | SIB SANKAR CHOWDHURY | 25.76 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Laying extra UPVC pipeline to cover Penchakola (298) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-05) |  |  | VCH/001809/2020-2021 | null | 25/03/2021 |  | SIB SANKAR CHOWDHURY | 3.9 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Laying extra UPVC pipeline to cover Dubli(299) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-06) |  |  | VCH/001810/2020-2021 | null | 25/03/2021 |  | SIB SANKAR CHOWDHURY | 4.03 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | SM/06798 | Retrofitting | Laying extra UPVC pipeline to cover Kharkasuli (300) , Marosol(302) , Katalda(343) , Beherbani (344) , Thakurbada (360) Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting JJM Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block Raipur ( Sl.No-07) |  |  | VCH/001811/2020-2021 | null | 25/03/2021 |  | SIB SANKAR CHOWDHURY | 4.28 | 0 | 0 | 0
Total | [13 empty] | 156.26 | 0 | 0