## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | SM/07244 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 07 ( Duldihi, Kamlagora, Kalapathar, Rangameta, Basulitara, Jambedia, & Anandapur). Total House Hold - 696 | Assistant Engineer | Junior Engineer | ORD/000493/2022-2023 | 372/BQA | 23/02/2023 | 09/04/2023 | TAPAS KUMAR HAZRA | 41.95 | 8.63 | 20.58 | 45
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | SM/07244 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme Kushtora ZONE- W under Bankura - l - ll & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - B Block - Bankura -l, name of OHR - Kushtora ZONE- W . - No.of Mouza :- 01 no., (Poryasol) Total House Hold - 50. |  |  | VCH/002993/2021-2022 | FHTC/22 | 22/03/2022 |  | KHAN ENTERPRISE | 2.75 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | SM/07244 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme Kustora ZONE- W under Bankura - l - ll & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - A Block - Bankura -l, name of OHR - Kushtora ZONE- W . - No.of Mouza :- 01 no., (Poryasol) Total House Hold - 60. |  |  | VCH/002994/2021-2022 | FHTC/22 | 22/03/2022 |  | KHAN ENTERPRISE | 4.24 | 0 | 0 | 0
Total | [13 empty] | 48.93 | 8.63 | 17.65