## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Kherkanali No.of Mouza :- 01 nos. ( Kaljuri)Total House Hold -120 nos. |  | Junior Engineer | ORD/000011/2022-2023 | 895/BQA | 14/04/2022 | 14/05/2022 | MOHAN KUMAR ROY | 14.36 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 21/03/2021 | M/S TARUN KUMAR PATRA | 96.69 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Additional UPVC Pipe Line for increasing pressure in existing distribution pipe line of Belboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000382/2021-2022 | 989/ BSD | 25/11/2021 | 10/12/2021 | M/S TARUN KUMAR PATRA | 2.11 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Restoration of concrete road at Belboni, Agya Nandapur & Kaljuri mouzas for construction and commissioning of "FHTC" (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000383/2021-2022 | 990/ BSD | 25/11/2021 | 10/12/2021 | M/S TARUN KUMAR PATRA | 4.94 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 41.56 | 17.72 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying HDPE Pipe Line to increase pressure at nabanda mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000448/2022-2023 | 621/BSD | 16/08/2022 | 06/09/2022 | KOUSHIK GUPTA KABIRAJ | 2.13 | 0 | 0 | 1
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying HDPE Pipe Line from Khyarkanali village to makurgram chatarkanali main road to increase pressure to kaljuri mouza of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. TSM/010428. |  | Junior Engineer | ORD/000498/2022-2023 | 376/BQA | 23/02/2023 | 09/04/2023 | MOHAN KUMAR ROY | 2.4 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  |  | VCH/001590/2021-2022 | FHTC/08 | 08/10/2021 |  | KASTURI ROY | 2.17 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No.- 11), |  |  | VCH/001591/2021-2022 | FHTC/08 | 08/10/2021 |  | M/S TARUN KUMAR PATRA | 4.94 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying extra HDPE pipeline to cover Jamda (38) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 10), |  |  | VCH/001592/2021-2022 | FHTC/08 | 08/10/2021 |  | M/S TARUN KUMAR PATRA | 4.96 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Koskunda), |  |  | VCH/001593/2021-2022 | FHTC/08 | 08/10/2021 |  | ASHISH KUMAR SAMANTA | 4.03 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 68 (Sl No of Work- 11) |  |  | VCH/001594/2021-2022 | FHTC/08 | 08/10/2021 |  | PRABIR BARDHAN | 0.77 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. , |  |  | VCH/001595/2021-2022 | FHTC/08 | 08/10/2021 |  | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.14 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. ( month of July - 2021) |  |  | VCH/001596/2021-2022 | FHTC/08 | 08/10/2021 |  | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.99 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Payment of Laboratory staff of RWS Bankura Sub - Division of Bankura Division, PHE Dte. (month of July - 2021 to Sep 2021) |  |  | VCH/001597/2021-2022 | FHTC/08 | 08/10/2021 |  | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.13 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Festival bonus for laboratory personnel engaged through NGO |  |  | VCH/001598/2021-2022 | FHTC/08 | 08/10/2021 |  | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.14 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Prayer for release fund for laboratory personal's for the month of Aug 2021 to Sep 2021 |  |  | VCH/001599/2021-2022 | FHTC/08 | 08/10/2021 |  | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.66 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Prayer for release fund for laboratory personal's for the month of May 2021 to Aug 2021 |  |  | VCH/001600/2021-2022 | FHTC/08 | 08/10/2021 |  | MALLABHUM MAHILA KALYAN SAMITY | 0.12 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Prayer for release fund for laboratory personal's for the month of June 2021 to Aug 2021 |  |  | VCH/001601/2021-2022 | FHTC/08 | 08/10/2021 |  | MALLABHUM MAHILA KALYAN SAMITY | 0.99 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Prayer for release fund for laboratory personal's for the month of April 2016 to jUNE 2021 , |  |  | VCH/001602/2021-2022 | FHTC/08 | 08/10/2021 |  | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.99 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- C) (Sl. No.- 13), |  |  | VCH/001635/2021-2022 | FHTC/29 | 29/10/2021 |  | M/S TARUN KUMAR PATRA | 3.63 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | SM/07315 | Retrofitting | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 12) |  |  | VCH/001785/2021-2022 | FHTC/29 | 29/10/2021 |  | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0 | 0
Total | [13 empty] | 386.71 | 41.56 | 10.75