## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  | Junior Engineer | ORD/000064/2021-2022 | 2198/BQA | 25/08/2021 | 24/09/2021 | M/S TARUN KUMAR PATRA | 112.13 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- Kamalpur (part), Total House Hold :-90 nos. |  | Junior Engineer | ORD/000227/2022-2023 | 248/KSD | 12/07/2022 | 27/07/2022 | M/S TARUN KUMAR PATRA | 3.87 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Laying UPVC pipe line from rising main air valve (near Ragametia) to Chhatapathor village to increase water pressure to Chhatapathor village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000307/2022-2023 | 362/KSD | 29/08/2022 | 18/09/2022 | DAUD ALI KHAN | 3.03 | 3.03 | 100 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Laying HDPE Pipe Line from Barabeda more to Mantumura & Patjuri Agaya to Kunkhri Basa to increase water pressure at Kunkhri Basa, Mantumura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000494/2022-2023 | 382/BQA | 23/02/2023 | 09/04/2023 | SAIKAT CHOWDHURY | 12.25 | 11.88 | 96.96 | 80
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Inter connection with rising main air valve to distribution line at two points near Barabeda & Ragametia village to increase water pressure of Subarda, Simla, Mantumura, Patju agaya, Ragametia of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000756/2022-2023 | 370/KSD | 29/08/2022 | 18/09/2022 | DAUD ALI KHAN | 3.01 | 3 | 99.68 | 100
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (Zone - D) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) s under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 1 no, Chhatpathor ( Part ), Total House Hold - 65 |  |  | VCH/000507/2021-2022 | null | 08/06/2021 |  | RAFIKUL MONDAL | 3.52 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamberia (179) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household - 160 Nos. |  |  | VCH/002629/2021-2022 | FHTC/24 | 24/02/2022 |  | TAPAS GHOSH | 10.78 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Laying extra HDPE pipe line from Maliara OHR site to Pingrui to increase pressure for mouza - Pingrui of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. part - B |  |  | VCH/002632/2021-2022 | FHTC/24 | 24/02/2022 |  | M/S NAYAN BARDHAN | 4.85 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Laying extra HDPE pipe line from Maliara OHR site to Pingrui to increase pressure for mouza - Pingrui of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Maliara (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. part - A sl no - 23 |  |  | VCH/002633/2021-2022 | FHTC/24 | 24/02/2022 |  | M/S NAYAN BARDHAN | 4.78 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002762/2021-2022 | FHTC/4 | 04/03/2022 |  | MUNMUN UPADHYAY | 34.71 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | SM/07320 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  |  | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 |  | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0 | 0
Total | [13 empty] | 266.62 | 17.91 | 6.72