## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 |  | Junior Engineer | ORD/000052/2020-2021 | 459/BQA | 05/02/2021 | 07/03/2021 | I.R.CONSTRUCTION | 11.01 | 1.76 | 16.01 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 |  | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 07/03/2021 | I.R.CONSTRUCTION | 28.91 | 0 | 0 | 95
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 02 no, (Jirra, Ramnathpur), Total House Hold - 645 nos. | Assistant Engineer | Junior Engineer | ORD/000096/2021-2022 | 2533/BQA | 23/09/2021 | 23/10/2021 | BISWARUP BOSE | 36.29 | 28.9 | 79.63 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Dismantling & reconstruction of concrete at Phaspa mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. [Jal Jeevan Mission (JJM) and JAL SWAPNA Fund] |  | Junior Engineer | ORD/000172/2022-2023 | 344/KSD | 16/08/2022 | 05/09/2022 | I.R.CONSTRUCTION | 3.61 | 3.61 | 99.97 | 80
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000173/2022-2023 | 346/BSD | 16/08/2022 | 05/09/2022 | I.R.CONSTRUCTION | 4.94 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Susunia (Upor Para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000175/2022-2023 | 348/KSD | 16/08/2022 | 05/09/2022 | I.R.CONSTRUCTION | 2.36 | 2.36 | 99.96 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Laying extra HDPE pipe line to cover Susunia mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000234/2021-2022 | 934/ BSD | 04/10/2021 | 19/10/2021 | I.R.CONSTRUCTION | 3.39 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Restoration of concrete at Susunia mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- D) under Saltora- Block, Saltora-Chhatna W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte |  | Junior Engineer | ORD/000235/2021-2022 | 935/ BSD | 04/10/2021 | 19/10/2021 | I.R.CONSTRUCTION | 4.11 | 4.09 | 99.6 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Laying of HDPE Pipe Line from Susunia More to Murut Baha Eco-Park at Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000751/2022-2023 | 636/BQA | 24/03/2023 | 08/05/2023 | SK SAMSA ALAM | 1.96 | 1.94 | 98.92 | 10
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debgram (296) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 201 Nos. |  |  | VCH/002294/2021-2022 | FHTC/31 | 31/01/2022 |  | SANJOY MONDAL | 9.21 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | SM/07341 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 4, Belebad,Moulahir, Mujrakundi Raj band Total House Hold -576 . |  |  | VCH/002494/2021-2022 | FHTC/3 | 03/02/2022 |  | M/S BIPUL BANERJEE | 20.03 | 0 | 0 | 0
Total | [13 empty] | 125.81 | 42.65 | 33.9