## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Laying HDPE pipeline from Husumdanga More to Dighi village to increase pressure in Dhajamanipur (87) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000012/2022-2023 | 918/BQA | 19/04/2022 | 19/05/2022 | MAYA CONSTRUCTION | 10.09 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Laying HDPE pipeline to increase pressure in Baharamuri (91) & Jibanpur (92) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000058/2022-2023 | 1682/BQA | 27/07/2022 | 26/08/2022 | SUBHADIP KOLEY | 9.22 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000062/2020-2021 | 474/BQA | 05/02/2021 | 07/03/2021 | DEBAKI RANJAN SARKAR | 23.18 | 1.77 | 7.62 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhajamanipur (87), Topabari (88), Kaliapathar (89) & Shyampur (90) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000125/2020-2021 | 182/BQA | 18/01/2021 | 17/02/2021 | SUBHADIP KOLEY | 21.98 | 0 | 0 | 60
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhajamanipur (87), Topabari (88), Kaliapathar (89) & Shyampur (90) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000126/2020-2021 | 183/BQA | 18/01/2021 | 17/02/2021 | GOPAL CHANDRA CHOUDHURY | 26.73 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baharamuri (91) mouza by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000135/2020-2021 | 192/BQA | 18/01/2021 | 17/02/2021 | GOPAL CHANDRA CHOUDHURY | 30.12 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Work Order for Household survey in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) |  | Junior Engineer | ORD/000355/2020-2021 | 41/KSD | 15/01/2021 | 16/03/2021 | TAPAS DEY | 0.38 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kaliapathar (89) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2) |  | Junior Engineer | ORD/000675/2021-2022 | 645/KSD | 17/09/2021 | 02/10/2021 | SUBHADIP KOLEY | 3.3 | 0 | 0 | 70
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 |  |  | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 |  | SANJOY MONDAL | 4.55 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Laying extra HDPE pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001023/2021-2022 | null | 16/09/2021 |  | GOPAL CHANDRA CHOUDHURY | 4.95 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Laying extra HDPE pipeline to cover Kaliapathar (89) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001024/2021-2022 | null | 16/09/2021 |  | GOPAL CHANDRA CHOUDHURY | 3.26 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Laying extra UPVC pipeline to cover Baharamuri (91) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001025/2021-2022 | null | 16/09/2021 |  | GOPAL CHANDRA CHOUDHURY | 3.11 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140, |  |  | VCH/001561/2021-2022 | FHTC/11 | 11/10/2021 |  | GANGADHAR MONDAL | 8.9 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., |  |  | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 |  | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baharamuri (91) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A |  |  | VCH/002985/2021-2022 | FHTC/24 | 24/03/2022 |  | GOPAL CHANDRA CHOWDHURY | 2.62 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baharamuri (91) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B |  |  | VCH/002986/2021-2022 | FHTC/24 | 24/03/2022 |  | GOPAL CHANDRA CHOWDHURY | 2.6 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87) & Kaliapathar (89) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002987/2021-2022 | FHTC/24 | 24/03/2022 |  | GOPAL CHANDRA CHOWDHURY | 2.01 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | SM/07363 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jibanpur (92) mouzas by retrofitting zone - Q ( Jambedia) ) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Hibandh under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B |  |  | VCH/002988/2021-2022 | FHTC/24 | 24/03/2022 |  | GOPAL CHANDRA CHOWDHURY | 2.72 | 0 | 0 | 0
Total | [13 empty] | 169.89 | 1.77 | 1.04