## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) | SM/07371 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) |  | Junior Engineer | ORD/000213/2021-2022 | 3049/BQA | 01/12/2021 | 31/12/2021 | M/S K.B.CONSTRUCTION | 69.82 | 21.75 | 31.15 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) | SM/07371 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 478/BQA | 04/03/2022 |  | Resource Division | 6.73 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) | SM/07371 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) |  |  | VCH/001453/2022-2023 | FHTC/06 | 06/12/2022 |  | M/S K.B.CONSTRUCTION | 15.31 | 0 | 0 | 0
Total | [13 empty] | 91.87 | 21.75 | 23.68