## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District | SM/08311 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone -C of Puncha &Zone -E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone -C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254) .No of House Hold - 2986 nos ).( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55) .No of House Hold - 4107 nos.). Total No of House Hold = ( 2986 nos +4107 nos ) =7093. Nos | Assistant Engineer | Junior Engineer | ORD/000024/2022-2023 | 1083/BQA | 12/05/2022 | 08/11/2022 | M/S TARUN KUMAR PATRA | 216.67 | 151.2 | 69.78 | 76
2 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District | SM/08311 | Retrofitting | Household survey in Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone- C of Puncha & Zone- E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone- C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254).No of House Hold - 2986 nos ). ( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55). No of House Hold- 4107 nos.). Total No of House Hold = (2986 nos + 4107 nos )= 7093. Nos. |  | Junior Engineer | ORD/000905/2021-2022 | 107/BSD | 28/01/2022 | 29/03/2022 | TAPAS DEY | 2.37 | 1.2 | 50.67 | 0
3 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District | SM/08311 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 2036/BQA | 29/09/2022 |  | Resource Division | 0.04 | 0 | 0 | 0
Total | [13 empty] | 219.07 | 152.4 | 69.57