## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 05 Nos. Total Household - 853 Nos. " |  | Junior Engineer | ORD/000039/2021-2022 | 1786/BQA | 09/07/2021 | 08/08/2021 | PARTHA PRATIM CHATAIT | 56.47 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II). No. of Mouza :-03 nos (Kadasole, Kamarsol, Ghutgaria), Total House Hold -1874 nos. |  | Junior Engineer | ORD/000039/2022-2023 | 1380/BQA | 27/06/2022 | 26/08/2022 | SIB SANKAR CHOWDHURY | 212.38 | 44.97 | 21.18 | 15
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000120/2022-2023 | 322/KSD | 01/08/2022 | 16/08/2022 | D. S. ENTERPRISE | 3.93 | 3.93 | 99.96 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Laying of extra UPVC pipe to increase water pressure at Majit mouza for rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - (I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000130/2022-2023 | 470/BSD | 06/06/2022 | 21/06/2022 | TAPAN KUMAR MANDAL | 4.98 | 4.98 | 100 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 22/01/2023 | NAYAN BARDHAN | 49.26 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180), Dhuliapur (177), Hariharpur (178), Tikarpara (182), Digpar (194), Kusmi (195) & Chakrasol (196) mouzas under Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 17 Nos. Total Household:- 2199 Nos. |  | Junior Engineer | ORD/000315/2021-2022 | 08/BQA | 03/01/2022 | 04/03/2022 | GOPAL CHANDRA CHOUDHURY | 148.6 | 148.36 | 99.84 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" |  | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 07/11/2020 | SOUMITRA BHATTACHARYA | 41.63 | 1.01 | 2.43 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-IV )Total House Hold - 139." |  | Junior Engineer | ORD/000336/2020-2021 | 1705/BQA | 08/12/2020 | 07/01/2021 | SUDAM KUMAR DAS | 9.89 | 9.42 | 95.2 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Work Order for Household survey in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180), Dhuliapur (177), Hariharpur (178), Tikarpara (182), Digpar (194), Kusmi (195) & Chakrasol (196) mouzas under Baricha, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12) |  | Junior Engineer | ORD/000596/2021-2022 | 798/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.73 | 0.73 | 100 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) |  | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.46 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Baricha (180), Dhuliapur (177) & Hariharpur (178) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 24) |  | Junior Engineer | ORD/000649/2021-2022 | 754/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.95 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | laying Extra UPVC pipeline to cover Palashbani (148) mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by retrofitting Zone-B (Tilaboni) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002772/2021-2022 | FHTC/5 | 05/03/2022 |  | SANJOY PATRA | 1.65 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Manjumara (Part-A), Total House Hold -125 |  |  | VCH/002774/2021-2022 | FHTC/5 | 05/03/2022 |  | TAPAN KUMAR SARKAR | 1.27 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | SM/09236 | Retrofitting | Supply & delivery of portable multi parameter water quality testing device of the device of rural drinking water sources of 146 Nos. GP in Bankura District of west Bengal under PHE Dte |  |  | VCH/002839/2021-2022 | FHTC/9 | 09/03/2022 |  | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 13.33 | 0 | 0 | 0
Total | [13 empty] | 553.52 | 213.4 | 38.55