## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | SM/09475 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 5 Nos. Total Household:- 640 Nos. |  | Junior Engineer | ORD/000413/2021-2022 | 410/BQA | 28/02/2022 | 30/03/2022 | SARKAR CONSTRUCTION | 37.44 | 11.07 | 29.56 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | SM/09475 | Retrofitting | Work Order for Household survey in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000606/2021-2022 | 804/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.21 | 0.21 | 99.69 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | SM/09475 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of UPVC pipeline in Kharika (27), Khapmayna (29) & Bankata (31) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000661/2022-2023 | 506/BQA | 13/03/2023 | 27/04/2023 | MANAS DEY | 3.56 | 3.19 | 89.44 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | SM/09475 | Retrofitting | Installation of stret stand post under Simlapal water supply scheme BRGF PH - I under Khatra Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000284/2022-2023 | FHTC/26 | 26/04/2022 |  | UTTAM KUMAR SINHAMAHAPATRA | 2.15 | 0 | 0 | 0
Total | [13 empty] | 43.37 | 14.47 | 33.35