## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza | SM/09535 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1713 nos. | Assistant Engineer | Junior Engineer | ORD/000414/2021-2022 | 435/BQA | 03/03/2022 | 17/04/2022 | SUBHANKAR BANERJEE | 100.63 | 43.51 | 43.24 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza | SM/09535 | Retrofitting | Household survey in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000894/2021-2022 | 94/BSD | 28/01/2022 | 29/03/2022 | TAPAS DEY | 0.57 | 0.1 | 17.05 | 20
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza | SM/09535 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 581/BQA | 17/03/2022 |  | Resource Division | 10.55 | 0 | 0 | 0
Total | [13 empty] | 111.75 | 43.61 | 39.02