## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | SM/09853 | Augmentation | Augmentation of Aguri Band Punisol piped water supply scheme in Onda Block of Bankura District under BRGF programme and providing Functional House Hold Tap Connection (FHTC) to each and every house hold within command area of Zone- C of the scheme. Name of Mouzas:- Chhagulia (3),Chandramonipur (4), Khapkata (5), Hirapur (6), Bhola (7), Jagannathpur (9), Dhandakeshabpur (56), Dubrakon (57), Nutangram (58), Saheb Ganja (59), Benajira (60), Panchami (61), Majura (62), Rampur (63), Hatbari (64), Tilabani (65), Ashnasol (66), Dhengakend (67), Baga Khulya Monoharpur (69), Gangadaspur (70), Basuara (71), Ekaria (72) & Kamala (73) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Nos. of House Hold= 3539 nos. | Assistant Engineer | Junior Engineer | ORD/000397/2021-2022 | 246\BQA | 09/02/2022 | 25/04/2022 | MRITUNJOY MUKHERJEE & CO. | 217.11 | 194.66 | 89.66 | 100
2 | BANKURA |  | Bankura Division | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | SM/09853 | Augmentation | Household survey in Chhagulia (3), Chandramonipur (4), Khapkata (5), Hirapur (6), Bhola (7), Jagannathpur (9), Dhandakeshabpur (56), Dubrakon (57), Nutangram (58), Saheb Ganja (59), Benajira (60), Panchami (61), Majura (62), Rampur (63), Hatbari (64), Tilabani (65), Ashnasol (66), Dhengakend (67), Baga Khulya Monoharpur (69), Gangadaspur (70), Basuara (71), Ekaria (72) & Kamala (73) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by Augmentation Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000899/2021-2022 | 90/BSD | 28/01/2022 | 29/03/2022 | TAPAS DEY | 1.18 | 1.11 | 94.07 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | SM/09853 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 452/BQA | 03/03/2022 |  | Resource Division | 19.44 | 0 | 0 | 0
Total | [13 empty] | 237.73 | 195.77 | 82.35