## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Laying DI (K7) & UPVC pipe line for distribution system with FHTC for the proposed Augmentation of Piped Water Supply Scheme for Kenjakura and its adjoining mouzas (JJM Revision) under Bankura Sadar Sub - Division, PHE Dte. (Part - A) & Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/10/2012) for Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas(JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000221/2022-2023 | 1972/BQA | 22/09/2022 | 17/10/2023 | M/S TARUN KUMAR PATRA | 343.73 | 125.3 | 36.45 | 70
2 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000234/2022-2023 | 357/BSD | 13/04/2022 | 28/04/2022 | MABCO CONSULTANT | 1.83 | 1.85 | 101.15 | 0
3 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Augmentation of piped water supply scheme for Kenjakura and its adjoining mouzas(JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000426/2023-2024 | 2009/BQA | 19/07/2023 | 14/04/2024 | M/S TARUN KUMAR PATRA | 176.63 | 0 | 0 | 40
4 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Laying of HDPE Pipe line,special repairing and ¿FHTC (Functional House Hold Tap Connection) at manoharpur village under KENJAKURA W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. | Assistant Engineer |  | ORD/000694/2022-2023 | 616/BQA | 23/03/2023 | 07/05/2023 | JAGADISH BANERJEE | 2.22 | 2.21 | 99.71 | 20
5 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Continuation for Diesel Ambassador Car equivalent luxury Car / Bolero / Scrpio etc. having license for contract carriage permit from the Regional Transport Authority for office use of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/12/2022 to 31/05/2023) | Assistant Engineer |  | ORD/000981/2022-2023 | 751/BSD | 28/11/2022 | 27/05/2023 | GOURANGA NANDI | 0.86 | 2.19 | 256.49 | 100
6 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 2146/BQA | 11/11/2022 |  | Resource Division | 54.83 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 40.87 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | SM/09877 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of piped water supply scheme for Kenjakura its adjoining mouzas (JJM Revision) under Bankura Mechanical Division PHE Dte Bankura-I Block- Dist -Bankura. | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 1170/BMD | 01/06/2023 | 28/11/2023 | M/S SOMA ENTERPRISES | 64.3 | 25.57 | 39.77 | 8
Total | [13 empty] | 685.25 | 157.12 | 22.93