## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipe line by PHE department in the different stretches in kotulpur kamarpukur road under Bishnupur division PHE Dte. |  |  | BILL/02190/2023-2024 | FHTC/12 | 01/12/2023 |  | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 13.06 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE Department from 0.800 km to 3.165 km in Kotulpur Indas road (MDR) under Bishnupur Division P.W.Dte. during the year 23-24 |  |  | BILL/02191/2023-2024 | FHTC/12 | 01/12/2023 |  | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 8.64 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Restoration work of side shoulder & Bituminious portion due to damage caused for the laying of pipe line by PHE Department from 29.09 km to 30.00 km in Bishnupur - Kotulpur road SH 2 UNDER Bishnupur division PWDte. during the year 23-24 |  |  | BILL/02194/2023-2024 | FHTC/12 | 01/12/2023 |  | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 15.7 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Restoration work of side shoulder due to probable caused for the laying of pipe line by PHE Department in the different stretches in Bishnupur - Kotulpur road sh 2 UNDER Bishnupur division PWDte. during the year 23-24 |  |  | BILL/02196/2023-2024 | FHTC/12 | 01/12/2023 |  | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 16.09 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Laying distribution system Augmentation of Kotulpur Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 1061/BQA | 10/05/2022 | 06/11/2022 | M/S TARUN KUMAR PATRA | 191.68 | 177.15 | 92.42 | 65
6 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Construction of boundary wall approx 170 mtr long for augmentation of Kotulpur water supply scheme (Head Work Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 57/BQA | 05/01/2023 | 04/02/2023 | ANNDAMAYEE CONSTRUCTION | 8.99 | 5.84 | 64.98 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Construction of boundary wall approx 70 mtr long for augmentation of Kotulpur water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 58/BQA | 05/01/2023 | 04/02/2023 | SK. ALAMGIR ALAM | 7.28 | 3.01 | 41.32 | 10
8 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Construction of boundary wall approx 70 mtr long for augmentation of Kotulpur water supply scheme (pump house no 3) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 59/BQA | 05/01/2023 | 04/02/2023 | LABIR MIRSHAD KHAN | 7.28 | 6.79 | 93.25 | 20
9 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Sinking of 1 No.Tube well 300 X 200 mm dia. X 165 Mtr. Depth Deep Tube well at Chadnighat by Rig boring for Kotulpur W/S Scheme Under Bishnupur Sub-Division of Bankura Division, PHE Dte. within Kotulpur Block, Dist :- BANKURA | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 60/BQA | 05/01/2023 | 04/02/2023 | OSMAN SEKH | 14.89 | 14.53 | 97.58 | 60
10 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | SOIL INVESTIGATION FOR 18 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KOTULPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 354/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 12.83 | 10.52 | 82 | 20
11 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | "Sinking of 1 No. Tube well 300 X 200 mm dia. X 165 Mtr. Depth Deep Tube well (at Opposite of Office cum Godown) by Rig boring for Kotulpur W/S Scheme Under Bishnupur Sub-Division of Bankura Division, PHE Dte. within Kotulpur Block, Dist :- BANKURA TSM No.- TSM/005085, SM/09981 , AAFS Project Id :- PH212246187S000" | Assistant Engineer | Junior Engineer | ORD/000556/2022-2023 | 520/BQA | 14/03/2023 | 07/04/2024 | TAPAS KUMAR HAZRA | 14.88 | 13.98 | 93.97 | 60
12 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Aditional work of Road Crossing for Jack Pussing of Augumention of Kotulpur Water Supply Scheme under Bishnupur Sub vision of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000870/2023-2024 | 3002/BQA | 03/11/2023 | 18/12/2023 | M/S TARUN KUMAR PATRA | 47.66 | 22.76 | 47.75 | 90
13 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.40 m x 3.6 m) for augmentation of Kotulpur Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. TSM No.- TSM/005085, SM/09981 , AAFS Project Id :- PH212246187S000 | Assistant Engineer | Junior Engineer | ORD/000922/2023-2024 | 3112/BQA | 09/11/2023 | 07/05/2024 | PRASANTA BHUIN | 6.54 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) of Kotulpur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block -Kotulpur, Name of OHR - Kotulpur, No. of Mouza :- 4 nos. i.e.Gogra-48,Ganti-49,Kotulpur (CT)-51,Shiromonipur-102. Total House Hold - 4060 | Assistant Engineer | Junior Engineer | ORD/001085/2021-2022 | 201/BQA | 01/02/2022 | 09/05/2024 | M/S CARE | 175.9 | 47.52 | 27.02 | 15
15 | BANKURA |  | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 111/BQA | 10/01/2024 |  | Resource Division | 25.01 | 0 | 0 | 0
16 | BANKURA |  | Bankura Mechanical | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Augmentation of Kotulpur Piped Water Supply Scheme. |  |  | BILL/00125/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
17 | BANKURA |  | Bankura Mechanical | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kotulpur H/W site under Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1070/BMSD | 05/07/2024 | 03/09/2024 | PRADIP KUMAR DHABAL | 4.38 | 0 | 0 | 0
18 | BANKURA |  | Bankura Mechanical | Augmentation of Kotulpur Piped Water Supply Scheme. | SM/09981 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000176/2023-2024 | 936/BMD | 12/05/2023 | 08/11/2023 | M/S SOMA ENTERPRISES | 45.85 | 34.16 | 74.52 | 75
Total | [13 empty] | 617.66 | 336.27 | 54.44