## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Karachmani Khayarsol Piped Water Supply Scheme | SM/12420 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KARACHMANI KHAYARSOL PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2023-2024 | 1053/BQA | 02/05/2023 | 27/01/2024 | PARAMESWAR CHOWDHURY | 239.64 | 35.16 | 14.67 | 3
2 | BANKURA | Sonamukhi | Bankura Division | Karachmani Khayarsol Piped Water Supply Scheme | SM/12420 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 23.46 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Karachmani Khayarsol Piped Water Supply Scheme | SM/12420 | New | Karachmani Khayarsol Piped Water Supply Scheme |  |  | BILL/01515/2023-2024 | BP-2023-24-116 | 29/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Karachmani Khayarsol Piped Water Supply Scheme | SM/12420 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Karachmani Khayarsol piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 654/BMD | 17/04/2023 | 14/10/2023 | UNITED TRADERS | 31.37 | 13.99 | 44.6 | 45
5 | BANKURA | Sonamukhi | Bankura Mechanical | Karachmani Khayarsol Piped Water Supply Scheme | SM/12420 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for proposed CWR water based Karachmani Khayarsol PWSS piped water supply scheme Block Sonamukhi under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000147/2024-2025 | 490/BMD | 09/07/2024 | 06/11/2024 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 24.25 | 0 | 0 | 0
Total | [13 empty] | 322.01 | 49.15 | 15.26