## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Hetia Piped Water Supply Scheme | SM/12425 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 11091.12 | 0 | 0 | 6
2 | BANKURA | Jaypur | Bankura Division | Hetia Piped Water Supply Scheme | SM/12425 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
3 | BANKURA | Jaypur | Bankura Division | Hetia Piped Water Supply Scheme | SM/12425 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 42.54 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Division | Hetia Piped Water Supply Scheme | SM/12425 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 884/BQA | 12/03/2024 |  | Resource Division | 14.49 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Hetia Piped Water Supply Scheme | SM/12425 | New | New service connection at Hetia Piped Water Supply Scheme t/w-II ,hetia gp of joypur block under BMD PHE Dte. |  |  | BILL/00140/2024-2025 | BP-2024-25-101 | 21/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.72 | 0 | 0 | null
6 | BANKURA | Jaypur | Bankura Mechanical | Hetia Piped Water Supply Scheme | SM/12425 | New | Hatia T/W -I |  |  | BILL/01506/2023-2024 | BP-2023-24-105 | 15/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.02 | 0 | 0 | 0
Total | [13 empty] | 11171.01 | 0 | 0