## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Hirbandh,Onda | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/13259 | New | New service connection for Pechara JIbandihi Moshiara Mini water supply scheme under Bankura Division PHE DTE |  |  | BILL/00152/2024-2025 | null | 16/05/2024 |  | HIRBANDH CCC | 0.11 | 0 | 0 | null
2 | BANKURA | Hirbandh,Onda | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/13259 | New | New service connection for Pechara JIbandihi Moshiara Mini water supply scheme under Bankura Division PHE DTE |  |  | BILL/00172/2024-2025 | BP-85/2024-25 | 29/05/2024 |  | HIRBANDH CCC | 0.11 | 0 | 0 | null
3 | BANKURA | Hirbandh,Onda | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/13259 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
Total | [13 empty] | 15500.84 | 0 | 0