## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Atra Piped Water Supply Scheme | SM/14000 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR ATRA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000376/2023-2024 | 2038/BQA | 24/07/2023 | 19/04/2024 | SIB SANKAR CHOWDHURY | 515.39 | 87.37 | 16.95 | 59
2 | BANKURA | Patrasayer | Bankura Division | Atra Piped Water Supply Scheme | SM/14000 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 2011/BQA | 26/07/2024 |  | Resource Division | 13.1 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Division | Atra Piped Water Supply Scheme | SM/14000 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 53.82 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Atra Piped Water Supply Scheme | SM/14000 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Atra Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 880/BMD | 04/05/2023 | 31/10/2023 | RAJIB COMPANY | 47 | 9.49 | 20.18 | 40
Total | [13 empty] | 629.31 | 96.85 | 15.39