## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Ramnagar Piped Water Supply Scheme | SM/14005 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RAMNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2023-2024 | 1972/BQA | 18/07/2023 | 30/12/2024 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 570.89 | 43.97 | 7.7 | 25
2 | BANKURA | Patrasayer | Bankura Division | Ramnagar Piped Water Supply Scheme | SM/14005 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 84.18 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Ramnagar Piped Water Supply Scheme | SM/14005 | New | New service connection for RAMNAGAR water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00020/2024-2025 | BP-2024-25-31 | 10/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0 | null
4 | BANKURA | Patrasayer | Bankura Mechanical | Ramnagar Piped Water Supply Scheme | SM/14005 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Ramnagar Piped water supply scheme Block : Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 770/BMD | 24/04/2023 | 21/10/2023 | RAJIB COMPANY | 46.94 | 9.46 | 20.16 | 40
Total | [13 empty] | 706.97 | 53.43 | 7.56