## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tungi (104), Rautara (105), Siromanipur (106), Raipur Bazar (139), Dharampur (140), Kajla (141), Kajalkura (142), Kamardiha (143), Kankrasol (144), Nayapara (170), Uparbanda (171), Dublala (172) & Simli (201) mouzas by retrofitting of Raipur Bazar and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 902/BQA | 20/04/2023 | 14/09/2025 | ASHIS KUMAR SAMANTA | 208.39 | 0 | 0 | 30
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Crossing road by 200 mm dia MS pipe by Jack pushing method, laying & fabrication of MS pipe and all allied works for Matgoda and its adjoining mouzas under water supply scheme for Left Out Mouzas of Raipur Block of under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (At Matgoda Bazar More) | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 936/BQA | 25/04/2023 | 25/05/2023 | SUBHADIP KOLEY | 9.02 | 9 | 99.73 | 100
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Crossing road by 200 mm dia MS pipe by Jack pushing method, laying & fabrication of MS pipe and all allied works for Matgoda and its adjoining mouzas under water supply scheme for Left Out Mouzas of Raipur Block of under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (At Niljora More) | Assistant Engineer | Junior Engineer | ORD/000074/2023-2024 | 937/BQA | 25/04/2023 | 25/05/2023 | GOPAL CHANDRA CHOWDHURY | 7.3 | 7.29 | 99.82 | 100
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamsol (145), Banpathari (146), Niljora (147), Kuldiha (148), Matgoda (162), Kelepara (165), Rajgan (166), Jadab Nagar (167), Jashpara (168) & Dubrajpur (169) mouzas by retrofitting of Matgoda and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1929/BQA | 13/07/2023 | 11/10/2023 | PARTHA PRATIM CHHATAIT | 207.77 | 45.05 | 21.68 | 95
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Buridhara (59), Chanpabani (60) & Chaturikalapathar (71) mouzas by retrofitting of Champabani and its adjoining mouzas Water Supply Scheme under Left Out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza - 3 Nos. Total Household- 335 Nos. | Assistant Engineer | Junior Engineer | ORD/000584/2022-2023 | 500/BQA | 13/03/2023 | 27/04/2023 | TAPAN KUMAR UPADHYAY | 23.67 | 0 | 0 | 75
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Culvert crossing by MS Pipe for Rising Main and Distribution Main with other ancillary works under Water supply scheme for Left out Mouzas of Raipur Block under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000990/2023-2024 | 3286/BQA | 30/11/2023 | 30/12/2023 | UTTAM KUMAR SINHAMAHAPATRA | 3.4 | 0 | 0 | 90
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | SM/14126 | Retrofitting | Work Order for Installation of scheme information board for 5 nos. site of Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block (SM/14126), 1 no. site of Retrofitting of Lurka (Zone-VB) Water Supply Scheme (BRGF Ph-I) (SM/14491) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001930/2024-2025 | 173\KSD | 07/03/2025 | 17/03/2025 | M/S ASHOK KUMAR DEY | 0.9 | 0 | 0 | 90
Total | [13 empty] | 460.46 | 61.34 | 13.32