## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Khundanga Piped Water Supply Scheme | SM/14482 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BAGDOBA & KHUNDANGA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 2332/BQA | 14/08/2023 | 10/05/2024 | GOPAL CHANDRA CHOWDHURY | 1262.72 | 0 | 0 | 35
2 | BANKURA | Kotulpur | Bankura Division | Khundanga Piped Water Supply Scheme | SM/14482 | New | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 29.17 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Khundanga Piped Water Supply Scheme | SM/14482 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Khundanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 873/BMD | 04/05/2023 | 31/10/2023 | M/S SWAPAN BANERJEE | 35.82 | 21.78 | 60.81 | 61
Total | [13 empty] | 1327.7 | 21.78 | 1.64