## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Additional laying of pipeline for providing FHTC (Functional House Hold Tap Connection) for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- V/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000071/2025-2026 | 1011/BQA | 25/04/2025 | 24/06/2025 | SANJOY PATRA | 15.89 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- V/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 1194/BQA | 22/05/2023 | 02/04/2025 | SANJOY PATRA | 232.69 | 112.3 | 48.26 | 81
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work order for Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- V/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2024-2025 | 1838/BQA | 12/07/2024 | 26/08/2024 | MOU CONSTRUCTION | 7.52 | 4.59 | 60.95 | 90
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-5A) (Sl. No. 09) |  | Junior Engineer | ORD/000630/2022-2023 | 187/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.53 | 3.26 | 92.54 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 16.10.2023 to 08.06.2024. | Assistant Engineer | Junior Engineer | ORD/001140/2023-2024 | 297\KSD | 05/10/2023 | 05/06/2024 | RAJ KUMAR BAURI | 0.09 | 0.02 | 25 | 90
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 12.02.2023 to 13.10.2023. | Assistant Engineer |  | ORD/001184/2022-2023 | 18/KSD | 08/02/2023 | 08/02/2024 | RAJ KUMAR BAURI | 0.09 | 0.09 | 100 | 90
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 225 Cum., staging height 20 Mtr.) including by pass arrangement, guard room and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- V/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001766/2024-2025 | 489/BQA | 25/02/2025 | 26/04/2025 | TAPAN KUMAR MANDAL | 11.03 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 09.06.2024 to 03.02.2025. | Assistant Engineer |  | ORD/002292/2024-2025 | 358\KSD | 05/06/2024 | 05/02/2025 | RAJ KUMAR BAURI | 0.09 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal w.e.f. 04.02.2025 to 21.10.2025 | Assistant Engineer |  | ORD/002293/2024-2025 | 72\KSD | 30/01/2025 | 30/09/2025 | RAJ KUMAR BAURI | 0.09 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 0.61 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 8.8 | 0 | 0 | 0
12 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | SM/15009 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000240/2023-2024 | 1125/BMD | 24/05/2023 | 23/06/2023 | SUTRADHAR TRADERS | 2.39 | 0 | 0 | 0
Total | [13 empty] | 282.83 | 120.27 | 42.52