## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Jibta Piped Water Supply Scheme | SM/15018 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR JIBTA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 1192/BQA | 22/05/2023 | 14/10/2024 | PRAVAT SARKAR | 368.38 | 66.07 | 17.93 | 71
2 | BANKURA | Kotulpur | Bankura Division | Jibta Piped Water Supply Scheme | SM/15018 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 2011/BQA | 26/07/2024 |  | Resource Division | 5.52 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Division | Jibta Piped Water Supply Scheme | SM/15018 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 31.95 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Mechanical | Jibta Piped Water Supply Scheme | SM/15018 | New | Jibta Piped Water Supply Scheme |  |  | BILL/01501/2023-2024 | BP-2023-24-96 | 15/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.55 | 0 | 0 | 0
5 | BANKURA | Kotulpur | Bankura Mechanical | Jibta Piped Water Supply Scheme | SM/15018 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Jibta piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 771/BMD | 24/04/2023 | 21/10/2023 | ABHIJIT MUKHERJEE | 31.26 | 13.14 | 42.03 | 43
Total | [13 empty] | 451.65 | 79.21 | 17.54