## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Kushadwip Piped Water Supply Scheme | SM/15266 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 13769.53 | 0 | 0 | 38
2 | BANKURA | Patrasayer | Bankura Division | Kushadwip Piped Water Supply Scheme | SM/15266 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 2527/BQA | 08/09/2023 |  | Resource Division | 10.29 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Division | Kushadwip Piped Water Supply Scheme | SM/15266 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 23 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Kushadwip Piped Water Supply Scheme | SM/15266 | New | Kushadwip Piped Water Supply Scheme |  |  | BILL/01655/2023-2024 | BP-2023-24-181 | 22/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.42 | 0 | 0 | 0
Total | [13 empty] | 13806.24 | 0 | 0