## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Akui Zone-A Water Supply Scheme | SM/16943 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AKUI ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000344/2023-2024 | 1968/BQA | 18/07/2023 | 13/04/2024 | S.N POLYMERS PVT LTD | 129.09 | 19.4 | 15.02 | 40
2 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-A Water Supply Scheme | SM/16943 | Augmentation | Augmentation of Akui Zone-A Water Supply Scheme |  |  | BILL/00184/2023-2024 | null | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-A Water Supply Scheme | SM/16943 | Augmentation | Load enhancement charges for AKUI ZONE A water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00438/2024-2025 | BP-2024-25-114 | 21/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0 | null
4 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-A Water Supply Scheme | SM/16943 | Augmentation | Augmentation of Akui Zone-A Water Supply Scheme |  |  | BILL/01626/2023-2024 | BP-2023-24-161 | 19/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.41 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-A Water Supply Scheme | SM/16943 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000358/2023-2024 | 1694/BMD | 28/07/2023 | 26/09/2023 | KINGKINI TRADERS | 41.83 | 8.47 | 20.26 | 40
Total | [13 empty] | 173.87 | 27.87 | 16.03